Table of Contents

Executive Summary	3

Community and Partner Engagement	4

Hendry-Glades Public Health System Task Force Members	4

CHIP Timeline	6

Glades County Snapshot	7

The Community Health Improvement Plan	9

Objective 1:  Improve the health of Glades County Residents by reducing the incidence of

weight-related health issues.	10

Objective 2:  Improve the health of Glades County residents by promoting healthier lifestyles

in Hendry County	12

Objective 3:  Contribute to a decrease in health issues related to residents engaging in risky

behaviors	13

Objective 4:  Expand and strengthen community partnerships and collaborations to build

capacity and better serve the needs of Glades County	15

Using the Plan and Next Steps	16

Executive Summary

The Hendry-Glades Public Health System Task Force, led by the Glades County Health Department, is pleased to present the Community Health Improvement Plan (CHIP) for Glades County.  This task force is made up of 36 public health partners and community members, all with the common goal of improving the health of Glades County.  The group met to better understand the current public health needs of Glades County residents and to develop a plan for community health improvement.  The process consisted of reviewing data, prioritizing health issues and planning the steps to address the needs in our community.  The product of this process is the Glades County Community Health Improvement Plan.  The intent of this plan is to identify priority goals and strategies while fostering community partnerships in order to improve the overall health of the community.  The Hendry-Glades Public Health System Task Force met from February through June, 2013 to update and improve the plan for Hendry County.  The Task Force has worked to review and compare the data contained in the 2011 and 2013 Community Health Assessments in preparation for the development of the CHIP.  The 2013 Glades County Community Health Assessment can be found on the Glades County Health Department’s website (www.doh.state.fl.us/chdGlades/) and on the Health Planning Council of Southwest Florida’s website (www.hpcswf.com/health-planning-services/community-health-assessments/).  The health priorities addressed in this plan emerged from the review of the data and the input and discussions of the Hendry-Glades Public Health System Task Force.

The Task Force worked to identify the top health priorities in an effort to ensure the CHIP addresses the priorities where we believe we can make a difference in an appropriate and effective manner.  The CHIP details the objectives, strategies, action steps, and measures that were developed to address the community’s health priorities.

Health Objectives Identified by Hendry-Glades Public Health System Task Force

- Objective 1:  Improve the health of Glades County Residents by reducing the incidence of weight-related health issues.

- Objective 2:  Improve the health of Glades County residents by promoting healthier lifestyles in Hendry County.

- Objective 3:  Contribute to a decrease in health issues related to residents engaging in risky behaviors.

- Objective 4:  Expand and strengthen community partnerships and collaborations to build capacity and better serve the needs of Glades County.

The Hendry-Glades Public Health System Task Force will continue to meet as we work toward our common goal of improving the health of Glades County.  Implementation of these objectives is already underway with positive results expected to follow soon.  We look forward to engaging the entire community in our efforts, and we welcome your participation and feedback in our community health improvement efforts.

Community and Partner Engagement

Hendry-Glades Public Health System Task Force Members

Glades County’s CHIP process engaged a large group of community residents and local public health system stakeholders.  Specifically:

( 33 community stakeholders – including representatives from the local hospital, healthcare providers, and social service organizations

( 3 community volunteers

Listed below are the individuals who worked on the improvement plan as a member of the Hendry-Glades Public Health System Task Force (H-G PHSTF).

Arlene Bettencourt

United Way of Hendry/Glades

Charlene Blum

Kim Kutch

Florida Department of Children and Families

Lisa Sands

Daisy Ellis

The Salvation Army

Lynn Beasley

Sandra Viall

Hendry Regional Medical Center

Nardina Johnson

Florida Community Health Center, Clewiston

Traci Thomas

Florida Community Health Center, Moore Haven

Ruby Nixon

Hope Connections

Maricela Morado

Healthy Start Coalition of Southwest Florida

Susan Harrelle

Hendry County Sheriff’s Department

Joe Hosick

Susan Shilharvey

Hendry Glades Behavioral Health

Norm Coderre

Children’s Medical Services

Jeannette Chelius

Susan Komen Foundation of Southwest Florida

Lupe Taylor

Hendry County Emergency Management

Janet Papinaw

Hendry County Board of County Commissioners

Donna Storter Long

Glades County Board of County Commissioners

Dana Breeden

Early Learning Coalition

Donna Akin

Hendry County Public Safety

Nancy Coker

Child Care of Southwest Florida

Dr. Jorge Quinonez

Family Health Center

Patricia K. Dobbins

Judy Paskvan

Jennifer Hood

Lynn Thomas

Brenda Barnes

Mary Ruth Prouty

The Florida Department of Health in Hendry and Glades Counties

Gail Holton

Senior Choices

Melissa Barraza

Lori Riddle

WIC Lee County

Raoul Batalier

The Hendry Glades Sunday News

Mary Bartoshuk

Community Volunteer

Linda Corbitt

Community Volunteer

Ron Stephens

Community Volunteer

CHIP Timeline

| May, 2011 | Began the Glades County Community Health Assessment by recruiting a team from the health department to partner with the Health Planning Council of Southwest Florida. |
| --- | --- |
| May, 2011 | Completed the Community Health Assessment with external and internal stakeholders. |
| June, 2011 | Received results of the Community Health Assessment from the Health Planning Council of Southwest Florida and met to discuss results. |
| August, 2011 | Provided seminars for health departments and community partners on customer service and time management. |
| January, 2012 | Strategic planning for Glades County Health Department. |
| May, 2012 | Recruited Hendry-Glades Public Health System Task Force (H-G PHSTF) participants to plan for CHIP. |
| June-July, 2012 | H-G PHSTF met to discuss and update plans. |
| September, 2012 | Final meeting for CHIP 2012. |
| January, 2013 | Internal health department team met to plan updates and improvements to original CHIP. |
| February-June, 2013 | H-G PHSTF met monthly during this period to update and improve the CHIP, approve the revised Community Health Assessment and set in motion plans to enact the CHIP. |
| June, 2013 | CHIP finalized. |

Glades County Profile

Demographics

- Residents of Glades County make up 0.07% of Florida’s total population.

- The county has a population density of about 17 persons per square mile compared to a state average of 357 persons per square mile.

- Males outnumber females in Glades County (57.8% vs. 42.2%).  Statewide the percentages are 48.9% male and 51.1% female.

Socioeconomics

- Residents living below poverty level:  22.2% Glades County vs. 17.0% Florida.

- Children (ages 0-17) living below poverty level:  33.6% Glades County vs. 25.1% Florida.

- Unemployment at 10.4% in Glades County is slightly lower than the state at 11.3%.

- Residents aged 25 and older who are high school graduates or higher is 71.3% in Glades County (2006-2010).  Statewide the percentage is 85.3%.

Health and Healthcare

- Glades County has a higher rate of infant deaths than the state as a whole (8.5 per 1,000 births vs. 6.6).

- Percent who smoke:  15.2% in Glades County vs. 17.1% in Florida.

- Men in Glades County are more likely to smoke than women (18.5% men vs. 10.8% women).

- Percent with diabetes:  11.5% in Glades County vs. 10.4% in Florida.

- Percent obese:  39.6% in Glades County vs. 27.2% in Florida.

- The most frequent causes of death in Glades County are heart disease and cancer.

- Among the types of cancer, lung cancer causes the highest number of deaths in Glades County.

- Glades County has been designated as a Health Professional Shortage Area for primary care.

- Glades County has been designated as a Health Professional Shortage Area for dental care for its low-income and migrant farmworker populations.

- The Glades/Hendry Catchment area has been designated as having a shortage of two mental health professionals.

The Community Health Improvement Plan

The Hendry-Glades Public Health System Task Force identified various health-related issues in the county.  In an effort to keep the Community Health Improvement Plan (CHIP) realistic and manageable, the Task Force narrowed these issues down to three health objectives for Glades County.  These focused on the identified priorities of weight-related health issues, preventative measures for healthier lifestyles, and risky behaviors that lead to health issues.  Also included was an objective aimed at strengthening the community partnerships that are the framework of a healthy community.

The sections below detail, for each of the four objectives:  strategies, action steps, and measures.

The objective is a general statement about a desired outcome.  It represents the end result the Task Force hopes to reach.

The strategies detailed in the plan represent ways the Task Force intends to achieve the objectives.

The action steps detailed in the plan provide the specific steps of how the strategies will be approached.

The measures detail more specifically what the community hopes to achieve.

| OBJECTIVE / STRATEGY / ACTION STEP | RESPONSIBLE PARTY | MEASURES | TARGET DATE | DATA SOURCE |
| --- | --- | --- | --- | --- |
| Objective 1: Improve the health of Glades County residents by reducing the incidence of weight-related health issues. |  |  |  |  |
|  | Strategy 1: Create a policy that all FDOH in H/G providers and outreach programs promote and use the 5-2-1-0 Childhood Obesity Prevention Program throughout Glades County. |  | Reduce the percentage of elementary school-aged children in the county that are overweight or obese from 42.6% to 40.0%. Aligns with Healthy People 2020 Objectives NWS-10, NWS-11, and National Prevention Strategy (NPS) Priority 'Active Living'. | June, 2015 | Glades County Health Management System (HMS) K-6 Data |
|  | Action Steps |
|  | • | Incorporate the 5-2-1-0 message into community outreaches, clinic settings, and county-wide outreach programs. | Mary Ruth Prouty, Jennifer Hood |  |  |  |
|  | • | Recruit community organizations and other local agencies to partner in the promotion of the campaigns. | Healthier Hendry Glades Task Force (HHGTF) |  |  |  |
|  | • | Develop and/or gather marketing materials related to the promotion of the community-wide campaigns. Materials will be branded with the Healthiest Weight Florida logo as possible. | Mary Ruth Prouty |  |  |  |
|  | Strategy 2: Promote the National Diabetes Prevention Program throughout Glades County. |  | Maintain or reduce the number of adults with diagnosed diabetes (11.5% as of 2010). Aligns with Healthy People 2020 Objective D-1. | June, 2015 | County-level data from the Behavioral Risk Factor Surveillance Survey (BRFSS) |
|  | Action Steps |
|  | • | Provide the National Diabetes Prevention Program for residents at risk to develop diabetes. | Hendry Regional Medical Center (HRMC) |  |  |  |
|  | • | Recruit community organizations and other local agencies to partner in the promotion of the campaigns. | HRMC, FDOH in H/G |  |  |  |
|  | • | Develop marketing materials related to the promotion of the community-wide campaigns. | HRMC, FDOH in H/G |  |  |  |
|  | Strategy 3: Increase awareness of healthy eating through community-wide campaigns. |  | Reduce the percentage of adults in the county who are overweight or obese from 75.1% to 73%. Aligns with Healthy People 2020 Objectives NWS-8, NWS-9, NWS-11, and NPS Priority 'Healthy Eating'. | June, 2015 | County-level data from the BRFSS |
|  | Action Steps |
|  | • | Distribute nutrition facts and healthy eating tips at community outreach events and at area clinics. | Outreach partners |  |  |  |
|  | • | Recruit community organizations and other local agencies to partner in the promotion of the campaigns. | HHGTF |  |  |  |
|  | • | Develop and/or gather, and distribute marketing materials related to the promotion of community-wide campaigns. | HHGTF |  |  |  |
| OBJECTIVE / STRATEGY / ACTION STEP | RESPONSIBLE PARTY | MEASURES | TARGET DATE | DATA SOURCE |
| Objective 2: Improve the health of Glades County residents by promoting healthier lifestyles in Glades County. |  |  |  |  |
|  | Strategy 1: Create awareness of available local health resources to encourage preventative care. |  | Reduce the percentage of adults in the county who report their overall health as "fair" or "poor" from 30.8% to 35%. | June, 2015 | County-level data from the BRFSS |
|  | Action Steps |
|  | • | Provide outreach to a minimum of two communities annually. | HHGTF |  |  |  |
|  | • | Promote United Way 2-1-1 as the information source. | United Way, HHGTF |  |  |  |
|  | Strategy 2: Create awareness of available local health resources to encourage current tobacco users to quit. |  | Increase the percentage of adults in the county who tried to quit smoking at least once in the past year from 52.0% to 60%. Aligns with Healthy People 2020 Objective TU-4, and NPS Priority 'Tobacco Free Living'. | June, 2015 | County-level data from the BRFSS |
|  | Action Steps |
|  | • | Promote smoking cessation with flyers, papers, and email distribution. | HRMC |  |  |  |
|  | • | Promote the Quit Line and 3 Ways to Quit. | HRMC, FDOH in H/G |  |  |  |
|  | • | Create a policy that all FDOH in H/G providers refer clients who use tobacco to HRMC for cessation classes. | FDOH in H/G |  |  |  |

| OBJECTIVE / STRATEGY / ACTION STEP | RESPONSIBLE PARTY | MEASURES | TARGET DATE | DATA SOURCE |
| --- | --- | --- | --- | --- |
| Objective 3: Contribute to a decrease in residents engaging in risky behaviors resulting in health issues. |  |  |  |  |
|  | Strategy 1: Promote the regular use of seatbelts. |  | Increase the percentage of adults who "always" or "nearly always" used seat belts when driving or riding in a car from 94.8% to 97%. Aligns with Healthy People 2020 Objective IVP-15, and NPS Priority 'Injury and Violence Free Living'. |  | County-level data from the BRFSS |
|  | Action Steps |
|  | • | Incorporate the promotion of regular use of seatbelts into county-wide outreach programs. | HHGTF |  |  |  |
|  | • | Recruit community organizations and other local agencies to partner in the promotion of the campaigns. | HHGTF |  |  |  |
|  | • | Develop and/or gather marketing materials related to the promotion of the community-wide campaigns. | HHGTF |  |  |  |
|  | • | Solicit the creation of a policy with Glades County Sheriff’s Department to issue citations for not using seatbelts. | HHGTF |  |  |  |
|  | Strategy 2: Reduce underage drinking. |  | Reduce the percentage of middle- and high school students who have drank alcohol in the past 30 days from the average of 23.8% to 22.0%. Aligns with Health People 2020 Objective SA-2, and NPS Priority Injury and Violence Free Living'. Reduce Substance Abuse Mental Health Services Administration (SAMHSA). | June, 2015 | Florida Youth Substance Abuse Survey |
|  | Action Steps |
|  | • | Provide Social Norms programs in the middle and high schools to educate students that the norm is not using alcohol. | Drug Free Hendry County |  |  |  |
|  | • | Recruit community organizations and other local agencies to partner in the promotion of the campaigns. | Drug Free Hendry County |  |  |  |
|  | • | Develop marketing materials related to the promotion of the community-wide campaigns. | Drug Free Hendry County |  |  |  |

| OBJECTIVE / STRATEGY / ACTION STEP | RESPONSIBLE PARTY | MEASURES | TARGET DATE | DATA SOURCE |
| --- | --- | --- | --- | --- |
| Objective 4: Expand and strengthen community partnerships and collaborations to build capacity and better serve the needs of Glades County. |  |  |  |  |
|  | Strategy 1: Evaluate the effectiveness of the Hendry-Glades Public Health System Task Force. |  | As defined by the Florida Department of Health evaluation template for partnerships. | June, 2015 | State-level data from the Florida Department of Health Data Template |
|  | Action Steps |
|  | • | Acquire evaluation. | FDOH in H/G, H-G PHSTF |  |  |  |

Using the Plan and Next Steps

This Community Health Improvement Plan is intended to be a starting point, a beginning that will lead to a healthier Glades County for future generations.  The next step in the process is to transform planning into action.  The Hendry-Glades Public Health System Task Force has already been working on specific programs to implement the strategies contained in the plan and improvements will soon follow.  The Glades County Health Department will continue to organize this community collaboration, as well as monitor and report back on the progress of initiatives and successes that this Community Health Improvement Plan will achieve.

The Glades County Health Department is dedicated to improving the health of Glades County residents, and will focus its efforts on collaborating with strategic partners as they work to achieve impacts in health outcomes.

For more information or to get involved in the county’s health improvement activities, please contact:

Mary Ruth Prouty

Florida Department of Health in Hendry and Glades Counties

Program Manager

Chronic Disease/Tobacco Prevention/Drug Free Hendry

1140 Pratt Blvd

LaBelle, Florida 33935

863 674-4056 ext 135

Mary_Prouty@doh.state.fl.us

# Text boxes

2013

Prepared by:

The Glades County Health Department and The Health Planning Council of Southwest Florida, Inc.

Glades County Florida

Community Health Improvement Plan